## Working Schedule
Task name | Time | Start | End | Engineer | %Load
Understand 8GESW Card |  | 2021-08-23 | 2021-08-24 | Ivan | 80
Understand SDH/SONET |  | 2021-08-25 | 2021-08-25 | Ivan | 80
Understand SNMPc |  | 2021-08-26 | 2021-08-26 | Ivan | 80
Understand AUTOIT |  | 2021-08-27 | 2021-08-27 | Ivan | 80
8GESW Firmware download |  | 2021-08-30 | 2021-09-03 | Ivan | 80
O9550 FW Upgrade and reset |  | 2021-09-06 | 2021-09-10 | Ivan | 80
Qe1 reset and Bert test |  | 2021-09-13 | 2021-09-17 | Ivan | 80
Understand AM3440 CCB |  | 2021-09-22 | 2021-09-24 | Ivan | 80
AM3440_A Tone Test |  | 2021-09-27 | 2021-09-27 | Ivan | 80
FXSA Bert |  | 2021-09-28 | 2021-10-01 | Ivan | 80
FXSA Signaling Test |  | 2021-10-04 | 2021-10-06 | Ivan | 80
FXOA Bert |  | 2021-10-07 | 2021-10-12 | Ivan | 80
FXOA Signaling Test |  | 2021-10-13 | 2021-10-18 | Ivan | 80
8EMA Bert |  | 2021-10-19 | 2021-10-22 | Ivan | 80
8EMA Signaling Test |  | 2021-10-25 | 2021-10-29 | Ivan | 80
MQE1 Bert |  | 2021-11-01 | 2021-11-02 | Ivan | 80
M1C37 Bert |  | 2021-11-03 | 2021-11-04 | Ivan | 80
6CD Bert |  | 2021-11-05 | 2021-11-08 | Ivan | 80
6UDTEA Bert |  | 2021-11-09 | 2021-11-10 | Ivan | 80
TDMOE Bert |  | 2021-11-11 | 2021-11-12 | Ivan | 80
Dual CCB Test |  | 2021-11-15 | 2021-11-17 | Ivan | 40
Download FW Test |  | 2021-11-15 | 2021-11-17 | Ivan | 40
RTB/Inband Test |  | 2021-11-18 | 2021-11-22 | Ivan | 80
Task name | Time | Start | End | Engineer | %Load
RS485 Test |  | 2021-11-23 | 2021-12-03 | Ivan | 80
O9550 MQT1 SNCP/Non-SNCP Test |  | 2021-12-01 | 2021-12-10 | Ivan | 80
Telnet/ SSH SNMP Port Test |  | 2021-12-13 | 2021-12-17 | Ivan | 80
Link Back-up protection Test |  | 2021-12-20 | 2021-12-24 | Ivan | 80
E1/T1 Port Protection Test |  | 2021-12-27 | 2021-12-30 | Ivan | 80
DS0-SNCP Test |  | 2021-01-03 | 2021-01-07 | Ivan | 80
PDH Ring Test |  | 2021-01-10 | 2021-01-14 | Ivan | 80
Task name | Time | Start | End | Engineer | %Load
(AM3440)DS0-SNCP Test Update |  | 2022-01-17 | 2022-01-21 | Ivan | 80
Study O9550 QE1 BERT Test |  | 2022-01-24 | 2022-01-28 | Ivan | 80
O9550 E1 Port Protection Test |  | 2022-02-07 | 2022-02-09 | Ivan | 80
O9550 DS0-SNCP Test |  | 2022-02-09 | 2022-02-11 | Ivan | 80
O9550 PDH Ring Protection Test |  | 2022-02-14 | 2022-02-16 | Ivan | 80
整合O9550 protection test |  | 2022-02-17 | 2022-02-18 | Ivan | 80
整合O9550 All test |  | 2022-02-21 | 2022-02-25 | Ivan | 80
O9550 bug verify |  | 2022-03-01 | 2022-03-04 | Ivan | 80
Task name | Time | Start | End | Engineer | %Load
AM3440 SSM Test |  | 2022-03-02 | 2022-03-16 | Ivan | 80
整合O9550語音卡測項 |  | 2022-03-17 | 2022-03-22 | Ivan | 80
AM3440 整合 子卡 upgrade /Bert |  | 2022-03-23 | 2022-03-25 | Ivan | 80
AM3440 Link backup add 子卡 reset/check clock status |  | 2022-03-28 | 2022-03-31 | Ivan | 80
AM3440 Port Protection add 1:1 rev and non-rev/add 子卡 reset/check clock status |  | 2022-03-29 | 2022-04-01 | Ivan | 80
AM3440 Port Protection add QE1/QT1/ TDMoEA |  | 2022-04-06 | 2022-04-08 | Ivan | 80
AM3440 Ds0-SNCP add 3T1/子卡 reset/check clock status |  | 2022-04-11 | 2022-04-15 | Ivan | 80
AM3440 PDH SSM Clock Test/add MQE1/MQT1/QT1 |  | 2022-04-18 | 2022-04-22 | Ivan | 80
Task name- AM3440 CCB Phase 4 | Time | Start | End | Engineer | %Load
AM3440 G.SHDSL / 6UDTEA / 6RS232 BERT |  | 2022-05-09 | 2022-05-10 | Ivan | 80
AM3440 FPGA Test( MAG / 6CDA / TTA / VOIP ) |  | 2022-05-17 | 2022-05-17 | Ivan | 80
AM3440 CCB In-Band Protection Test |  | 2022-05-20 | 2022-05-20 | Ivan | 80
AM3440 CCB add initial(register) card , unregister card in test cases |  | 2022-05-23 | 2022-05-23 | Ivan | 80
Task name- O9550 CC4A Phase 4 AM3440 CC4A Phase 4 | Time | Start | End | Engineer | %Load
O9550 DS0-SNCP add different mode |  | 2022-04-25 | 2022-04-29 | Ivan | 80
O9550 Port Protection add QT1/TDMoEA, QE1/TDMoEA |  | 2022-05-02 | 2022-05-06 | Ivan | 80
09550 TDMoEA VLAN ID Test |  | 2022-05-05 | 2022-05-06 | Ivan | 80
09550 Controller Loopback Test(data/unframe) |  | 2022-05-11 | 2022-05-13 | Ivan | 80
O9550 Controller Loopback Test(voice) |  | 2022-05-16 | 2022-05-17 | Ivan | 80
SNMP V3 Study |  | 2022-05-18 | 2022-05-19 | Ivan | 80
O9550 Link Backup Test (FOM/FE1/FT1) |  | 2022-05-24 | 2022-05-27 | Ivan | 80
O9550 QE1/QT1/FOM Remote Loopback Test |  | 2022-05-27 | 2022-05-31 | Ivan | 80
O9550 FileTransfer( upload/download , retrieve/store backup or current config) |  | 2022-05-30 | 2022-06-02 | Ivan | 80
O9550 Telnet/SSH Test + User Create |  | 2022-06-01 | 2022-06-02 | Ivan | 80
O9550 RTA/RTB In-band Protection |  | 2022-06-06 | 2022-06-10 | Ivan | 80
Task name- AM3440 CC4A Phase 5 | Time | Start | End | Engineer | %Load
AM3440 CC4A MSP 1+1 Protection in Vertical group |  | 2022-06-13 | 2022-06-17 | Ivan | 80
AM3440 CC4A DCC (to cpu) with J0,J1,J2 Overhead Test |  | 2022-06-20 | 2022-06-24 | Ivan | 80
AM3440 CC4A 4C37 Bert Test |  | 2022-06-27 | 2022-06-28 | Ivan | 80
AM3440 CC4A MQE1 SNCP (Data) Test |  | 2022-06-29 | 2022-07-01 | Ivan | 80
AM3440 CC4A MQE1 SNCP (Voice) Test |  | 2022-07-04 | 2022-07-06 | Ivan | 80
AM3440 CC4A FXSA Self Test |  | 2022-07-07 | 2022-07-08 | Ivan | 80
AM3440 CC4A EMA Self Test |  | 2022-07-11 | 2022-07-12 | Ivan | 80
AM3440 CC4A FXOA Self Test |  | 2022-07-13 | 2022-07-15 | Ivan | 80
AM3440 CC4A MAGA Self Test |  | 2022-07-18 | 2022-07-20 | Ivan | 80
AM3440 CC4A Organize Report / Test issue / ECR issue due to MSRD |  | 2022-07-21 | 2022-07-26 | Ivan | 80
AM3440 CC4A Integrate Report |  | 2022-07-27 | 2022-07-29 | Ivan | 80
Task name- AM3440 CC4A Phase 6 | Time | Start | End | Engineer | %Load
AM3440 CC4A 50 ms Protection Switch Test (IP 6704) |  | 2022-08-01 | 2022-08-03 | Ivan | 80
AM3440 CC4A Different VTE frame alarm detect Test |  | 2022-08-04 | 2022-08-05 | Ivan | 80
AM3440 CC4A QFXSA Ring Detect Test |  | 2022-08-08 | 2022-08-09 | Ivan | 80
AM3440 CC4A QEMA Relay Close Test |  | 2022-08-10 | 2022-08-11 | Ivan | 80
AM3440 CC4A ABRA Protection Test |  | 2022-08-15 | 2022-08-16 | Ivan | 80
AM3440 CC4A Reports Organize |  | 2022-08-17 | 2022-08-19 | Ivan | 80
AM3440 CC4A MSP/SNCP APS command |  | 2022-08-22 | 2022-08-26 | Ivan | 80
AM3440 CC4A Signaling through VTE test |  | 2022-08-29 | 2022-09-02 | Ivan | 80
6CDA Self Test |  | 2022-09-05 | 2022-09-09 | Ivan | 80
6UDTEA Self Test |  | 2022-09-12 | 2022-09-16 | Ivan | 80
Task name- AM3440 CCB/CC4A MQE1/MQT1 New Cards Detailed Autotest | Days | Start | End | Engineer | %Load
MQE1 Line Control Test | 5 | 2022-09-19 | 2022-09-23 | Ivan | 80
MQT1 Line Control Test | 5 | 2022-09-26 | 2022-09-30 | Ivan | 80
MQE1 Command Control Test | 5 | 2022-10-03 | 2022-10-07 | Ivan | 80
MQE1 Clock Test | 3 | 2022-10-11 | 2022-10-13 | Ivan | 80
MQE1 TSI Signaling Test | 2 | 2022-10-13 | 2022-10-14 | Ivan | 80
MQE1 System Setup Test (Frame) | 2 | 2022-10-17 | 2022-10-18 | Ivan | 80
MQE1 System Setup Test (FDL+Remote loopback) | 3 | 2022-10-19 | 2022-10-21 | Ivan | 80
MQE1 1+1 Protection (SSM Clock check) | 5 | 2022-10-24 | 2022-10-28 | Ivan | 80
MQT1 Clock Test | 3 | 2022-10-31 | 2022-11-02 | Ivan | 80
MQT1 TSI Signaling Test | 2 | 2022-11-03 | 2022-11-04 | Ivan | 80
MQT1 System Setup Test (Frame) | 2 | 2022-11-07 | 2022-11-08 | Ivan | 80
MQT1 System Setup Test (FDL+Remote loopback) | 3 | 2022-11-09 | 2022-11-11 | Ivan | 80
MQT1 1+1 Protection (SSM Clock check) | 5 | 2022-11-14 | 2022-11-18 | Ivan | 80
MQE1 + MQT1 Regression Test | 23 | 2022-11-21 | 2022-12-21 | Ivan | 80
Set up O9550-CC4A Autotest Environment in LAB/ O9500R-PTN Voice-card Autotest Environment in Mini-LAB | 7 | 2022-12-22 | 2022-12-30 | Ivan | 80
[Addendum] MQTE Warm Reset/Cold Reset/Power Relay Test | 4 | 2023-01-03 | 2023-01-06 | Ivan | 80
Task name- O9500R-PTN Autotest For FAA | Days | Start | End | Engineer | %Load
O9500R-PTN OCUDP Working / System Warm Reset Test | 3 | 2023-01-09 | 2023-01-11 | Ivan | 80
O9500R-PTN SFTP Download FW Test | 2 | 2023-01-12 | 2023-01-13 | Ivan | 80
O9500R-PTN Regression Test For FAA | 4 | 2023-01-16 | 2023-01-19 | Ivan | 80
O9500R-PTN G.SHDSL - H3300 Test | 5 | 2023-01-30 | 2023-02-03 | Ivan | 80
O9500R-PTN PUT Test Report | 5 | 2023-02-06 | 2023-02-10 | Ivan | 80
O9500 Autotest Technology Summit (KODA) | 5 | 2023-02-13 | 2023-02-17 | Ivan | 80
O9500R-PTN Master Plan | 5 | 2023-03-27 | 2023-03-31 | Ivan | 80
Task name- WDM-1800 Autotest | Days | Start | End | Engineer | %Load
WDM1800 Download FW (TFTP/SFTP) | 3 | 2023-02-20 | 2023-02-22 | Ivan | 80
WDM1800 8TP/Mux-Demux BERT (Fixed interface setup) | 2 | 2023-02-23 | 2023-02-24 | Ivan | 80
WDM1800 8TP/Mux-Demux BERT (not Fixed interface setup) | 3 | 2023-03-01 | 2023-03-03 | Ivan | 80
WDM1800 Group member Test | 2 | 2023-03-06 | 2023-03-07 | Ivan | 80
WDM1800 Register Test | 2 | 2023-03-08 | 2023-03-09 | Ivan | 80
WDM1800 Ctrl Reset/power on off Test | 3 | 2023-03-10 | 2023-03-14 | Ivan | 80
WDM1800 Ctrl Download FAE Module/ Upload download config Test | 3 | 2023-03-15 | 2023-03-17 | Ivan | 80
WDM1800 Regression Test | 5 | 2023-03-20 | 2023-03-24 | Ivan | 80
WDM1800 Master Plan | 3 | 2023-04-06 | 2023-04-10 | Ivan | 80
WDM1800 MSRD Presentation Preparing | 5 | 2023-04-11 | 2023-04-17 | Ivan | 80
Task name- V4150 Autotest | Days | Start | End | Engineer | %Load
V4150 Download CCA FW(TFTP) | 4 | 2023-04-18 | 2023-04-21 | Ivan | 40
V4150 Register Card | 2 | 2023-04-24 | 2023-04-25 | Ivan | 40
V4150 E1 PDH BERT | 3 | 2023-04-26 | 2023-04-28 | Ivan | 40
V4150 E1 PRCT BERT | 2 | 2023-05-02 | 2023-05-03 | Ivan | 40
V4150 T1 PDH BERT | 2 | 2023-05-04 | 2023-05-05 | Ivan | 40
V4150 T1 PRCT BERT | 2 | 2023-05-08 | 2023-05-09 | Ivan | 40
V4150 Schedule Ajustment | 7 | 2023-05-23 | 2023-05-31 | Ivan | 40
V4150 Build Regression Platform | 4 | 2023-07-03 | 2023-07-07 | Ivan | 40
V4150 Regression Clock Test | 4 | 2023-07-03 | 2023-07-07 | Ivan | 20
V4150 Regression TFTP/SFTP Test | 4 | 2023-07-03 | 2023-07-07 | Ivan | 20
V4150 Regression Load Default Check LED Test | 4 | 2023-07-10 | 2023-07-14 | Ivan | 30
V4150 Regression Map Activate/Copy Test | 4 | 2023-07-10 | 2023-07-14 | Ivan | 30
V4150 Regression Download/Retrieve Configure Test | 4 | 2023-07-10 | 2023-07-14 | Ivan | 20
V4150 Regression Produce Report to MSRD | 4 | 2023-07-17 | 2023-07-21 | Ivan | 40
Military Service | 4 | 2023-07-24 | 2023-07-28 | Ivan | 80
V4150 SSH Test | 3 | 2023-07-31 | 2023-08-02 | Ivan | 40
V4150 E1/T1 50ms Test | 3 | 2023-08-07 | 2023-08-09 | Ivan | 80
V4150 T3/B155 50ms Test | 3 | 2023-08-10 | 2023-08-11 | Ivan | 20
V4150 E1/T1 Map Add/Delete with Configure Change Test | 2 | 2023-08-10 | 2023-08-11 | Ivan | 60
V4150 E1/T1 External Clock Test | 6 | 2023-08-14 | 2023-08-21 | Ivan | 20
V4150 E1/T1 TSI Data Test | 6 | 2023-08-14 | 2023-08-21 | Ivan | 20
Task name- AM3440 CCB SW Review | Days | Start | End | Engineer | %Load
AM3440 CCB SW Architecture Paper Review | 4 | 2023-04-18 | 2023-04-21 | Ivan | 40
AM3440 CCB SW #ECR:23000109 | 2 | 2023-04-24 | 2023-04-25 | Ivan | 40
AM3440 CCB SW #ECR:23000109-MIB | 3 | 2023-04-26 | 2023-04-28 | Ivan | 40
AM3440 CCB SW Code Warrior Learning | 3 | 2023-09-01 | 2023-09-05 | Ivan | 80
AM3440 CCB SW Makefile Study | 3 | 2023-09-06 | 2023-09-08 | Ivan | 80
AM3440 CC4A Fixed CheckMarx Problems | 5 | 2023-09-11 | 2023-09-15 | Ivan | 80
AM3440 CCB SW Startup Programming & Fieldmode Study | 5 | 2023-09-18 | 2023-09-22 | Ivan | 80
AM3440 CCB AMX User Guide Study | 5 | 2023-09-25 | 2023-09-28 | Ivan | 40
AM3440 CCB SW VT-100 Display Study | 5 | 2023-09-25 | 2023-09-28 | Ivan | 40
AM3440 CCB SW Telnet/SSH/Console Study | 5 | 2023-10-02 | 2023-10-06 | Ivan | 80
AM3440 CCB SW RS485/VR485 Study | 5 | 2023-10-09 | 2023-10-13 | Ivan | 80
AM3440 CCB SW MPC8248 Study | 5 | 2023-10-16 | 2023-10-20 | Ivan | 80
AM3440 CCB SW CCB-Boot Study | 5 | 2023-10-23 | 2023-10-27 | Ivan | 80
AM3440 CCB SW CCB-Drive Study | 5 | 2023-10-30 | 2023-10-31 | Ivan | 80
Task name- WDM1800 SW Review | Days | Start | End | Engineer | %Load
WDM1800 Xilinx SDK Prepare | 3 | 2023-11-01 | 2023-11-03 | Ivan | 80
WDM1800 ECR Fixed | 5 | 2023-11-06 | 2023-11-10 | Ivan | 80
WDM1800 Add boot bank change | 2 | 2023-11-13 | 2023-11-14 | Ivan | 80
WDM1800 Add copy firmware to standby | 3 | 2023-11-15 | 2023-11-17 | Ivan | 80
WDM1800 HTTP and SSL Problem | 5 | 2023-11-20 | 2023-11-24 | Ivan | 80
WDM1800 Muxponder SFTP Download issue | 2 | 2023-11-27 | 2023-11-28 | Ivan | 80
WDM1800 Muxponder Group & Remote Info issue | 2 | 2023-11-29 | 2023-11-30 | Ivan | 80
Task name- AM3440 CC4A V1.20.01 batch | Days | Start | End | Engineer | %Load
Porting 6UDTEA new function | 2 | 2023-12-01 | 2023-12-04 | Ivan | 80
Porting 4T1 new function | 2 | 2023-12-05 | 2023-12-06 | Ivan | 80
Porting 8DC new function | 2 | 2023-12-07 | 2023-12-08 | Ivan | 80
Porting 2GH new function | 2 | 2023-12-11 | 2023-12-12 | Ivan | 80
Porting RTB new function | 3 | 2023-12-13 | 2023-12-15 | Ivan | 80
Porting 8DBRA new function | 2 | 2023-12-18 | 2023-12-19 | Ivan | 80
Porting 1FOMB new function | 2 | 2023-12-20 | 2023-12-21 | Ivan | 80
MR | 6 | 2023-12-22 | 2023-12-29 | Ivan | 80
Task name- O9400R-PTN Autotest | Days | Start | End | Engineer | %Load
O9400R-PTN FW Download Test | 2 | 2023-05-10 | 2023-05-11 | Ivan | 80
O9400R-PTN Register Card Test | 1 | 2023-05-12 | 2023-05-12 | Ivan | 80
O9400R-PTN MSP 1+1 Test | 2 | 2023-05-15 | 2023-05-16 | Ivan | 80
O9400R-PTN E1 Protection Test | 2 | 2023-05-17 | 2023-05-18 | Ivan | 80
O9400R-PTN T1 Protection Test | 2 | 2023-05-19 | 2023-05-22 | Ivan | 80
O9400R-PTN Power On/Off Test | 2 | 2023-05-23 | 2023-05-24 | Ivan | 40
O9400R-PTN Regression Environment Design | 5 | 2023-05-25 | 2023-05-31 | Ivan | 40
O9400R-PTN Modify From Joseph O9500R-PTN Regression Test-E1/T1 | 3 | 2023-06-01 | 2023-06-05 | Ivan | 60
O9400R-PTN Modify From Joseph O9500R-PTN Regression Test-E3/T3 | 4 | 2023-06-06 | 2023-06-09 | Ivan | 60
O9400R-PTN Modify From Joseph O9500R-PTN Regression Test-B16 | 5 | 2023-06-12 | 2023-06-16 | Ivan | 60
O9400R-PTN Modify From Joseph O9500R-PTN Regression Test-8GE | 5 | 2023-06-19 | 2023-06-23 | Ivan | 60
O9400R-PTN All Card Regression Test | 5 | 2023-06-26 | 2023-06-30 | Ivan | 60
O9400R-PTN Regression Produce Report to MSRD | 4 | 2023-07-17 | 2023-07-21 | Ivan | 40
O9400R-PTN SSH Test | 3 | 2023-07-31 | 2023-08-02 | Ivan | 40
O9400R-PTN Joseph 8GE Regression Test | 2 | 2023-08-03 | 2023-08-04 | Ivan | 80
O9400R-PTN E1/T1 External Clock Test | 6 | 2023-08-14 | 2023-08-21 | Ivan | 20
O9400R-PTN E1/T1 TSI Data Test | 6 | 2023-08-14 | 2023-08-21 | Ivan | 20
OpenVNS Automation Test | 4 | 2023-08-28 | 2023-08-31 | Ivan | 80
Task name-WDM1800 CTRL V1.05.03 Batch Release | Days | Start | End | Engineer | %Load
WDM1800 CTRL ECR Bug Fixing | 9 | 2024-01-02 | 2024-01-12 | Ivan | 80
WDM1800 OTDR ECR Bug Fixing | 13 | 2024-01-15 | 2024-01-31 | Ivan | 20
WDM1800 Transponder ECR Bug Fixing | 13 | 2024-01-15 | 2024-01-31 | Ivan | 20
WDM1800 25G-Transponder ECR Bug Fixing | 13 | 2024-01-15 | 2024-01-31 | Ivan | 20
WDM1800 Muxponder ECR Bug Fixing | 20 | 2024-01-15 | 2024-02-16 | Ivan | 20
Task Name | Time | Start | End | Engineer | %Load
Merge CCPA |  | 1月19日 | 1月19日 | Riker | 50%
SNTP 2036 issue |  | 1月22日 | 1月23日 | Riker | 50%
ECR |  | 1月24日 | 1月31日 | Riker | 50%
MR |  | 2月1日 |  |  | 20%
Porting FXSA-02/03 | 2 | 2月1日 | 2月2日 | Kyle | 80
Integration Test | 1 | 2月5日 | 2月5日 | Kyle | 80
MR | 10 | 2月6日 | 2月27日 | Kyle | 20
NFS |  | 2月1日 | 2月5日 | Johnson | 50%
ECR |  | 2月6日 | 2月21日 | Johnson | 50%
12FXS-02/03 |  | 2月22日 | 3月8日 | Johnson | 50%
Regression |  | 3月11日 | 3月15日 | Johnson | 50%
MR |  | 3月18日 |  | Johnson | 20%
NFS-SNMPV3 by OverWrite |  | 2月19日 | 2月23日 | Joseph | 50%
12FXS-02/03 |  | 2月26日 | 2月29日 | Joseph | 50%
ECR |  | 3月1日 | 3月6日 | Joseph | 20%
Regression |  | 3月7日 | 3月8日 | Joseph | 20%
MR |  | 3月11日 |  | Joseph | 50%
Regression |  | 2024-02-19 | 2024-02-29 | Ivan | 20%
Task name-G7800 B2G5-32TE Autotest | Days | Start | End | Engineer | %Load
Learn plink | 2 | 2024-02-19 | 2024-02-20 | Ivan | 60%
Download B2G5 autotest | 3 | 2024-02-21 | 2024-02-23 | Ivan | 20%
Download 32TE autotest | 3 | 2024-02-21 | 2024-02-23 | Ivan | 10%
Download CC2 autotest | 3 | 2024-02-21 | 2024-02-23 | Ivan | 10%
Learn Python to generate Excel Sheet | 6 | 2024-02-21 | 2024-02-29 | Ivan | 40%
Review O9500R-PTN MPLS-TP autotest spec. | 3 | 2024-02-26 | 2024-02-29 | Ivan | 60%
B2G5 E1 SAToP data path verify | 11 | 2024-03-01 | 2024-03-15 | Ivan | 40%
32TE E1 SAToP data path verify | 11 | 2024-03-01 | 2024-03-15 | Ivan | 40%
B2G5 T1 SAToP data path verify | 10 | 2024-03-18 | 2024-03-29 | Ivan | 40%
32TE T1 SAToP data path verify | 10 | 2024-03-18 | 2024-03-29 | Ivan | 40%